## AdoptionChecklist
Microsoft 365 Copilot
Adoption Planning Checklist - Abbreviated
Utilize this checklist to begin your planning process. Import into Microsoft Lists or add additional content as needed in your organization.
Task ID | Task | Description | Status | Assigned To | Due Date | Start Date | End Date
1 | Identify technology enablement team members | Identify adoption specialist / user experience staff, IT technical staff, executives, and other stakeholders for the core team | Not Started
2 | Participate in Art of the Possible workshop | Understand the key capabilities of Microsoft 365 Copilot and prioritize business scenarios | Not Started
3 | Design user experience strategy including end user support and readiness communications plan | Use Microsoft documentation and Copilot Center of Excellence for design guidance | Not Started
4 | Complete technical readiness work including configuration of Center of Excellence* | Prepare tenant for healthy deployment per Microsoft recommendations | Not Started
5 | Select early adopter / rapid deployment program users | Select employees who will use new capabilities and share feedback | Not Started
6 | Train Copilot Flight Crew (Champions) | Onboard and train peer to peer Champion team to provide support and guidance during end user onboarding and initial usage of Copilot features | Not Started
7 | Schedule learning series activities | “Copilot for You” and “Copilot for your Team” hands-on learning series with Copilot Lab. Followed by per app and AI-ready scenario sessions. Schedule office hours for support and prompt sharing. | Not Started
8 | Deploy licenses | In the Microsoft Admin Center | Not Started
9 | Schedule executive onboarding | White glove onboarding sessions for executives | Not Started
10 | Kick off user communications series with welcome email from Exec Stakeholder and invite into Community of Practice | Implement ongoing communications to new users to drive learning series attendance, community engagement and product usage | Not Started
11 | Schedule feedback roundtables and community calls | Provide employee only opportunities to provide feedback on Copilot features | Not Started
12 | Review Adoption Score reporting with enablement team & exec staekholders | Establish collaboration best practice baselines; drive meaningful awareness of success. | Not Started
13 | Create feedback analysis workstream | Participate in internal and Microsoft-led feedback sessions | Not Started
14 | Implement executive white glove sessions | Invite executive level staff to thought | Not Started
15 | Conduct service health review | Review service usage & health against selected AI-ready scenarios and support ticket volumes and open issues. Validate AI-ready roadmap. | Not Started
16 | Nominate success stories | Identify successful scenarios that have been impacted by Copilot usage to share | Not Started

## Values (hidden)
Status
Not Started
In Progress
Pending Info
Blocked
Completed
Deferred